|  | AgroDoc AI Your Farm. Our Doctor. Grant Application — AI-Powered Agricultural Advisory Platform Submitted to: IITA / Bill & Melinda Gates Foundation ¦ April 2026 ¦ Lead Applicant: Adegbegi Martins Maxwell |
| --- | --- |

# Project Summary

AgroDoc AI ("Your Farm. Our Doctor.") is a multilingual, AI-powered farm advisory platform for Nigerian smallholder farmers. Using Claude AI (Anthropic), the platform enables farmers to photograph diseased crops, sick poultry, fish, or livestock and receive instant, actionable diagnoses in English, Nigerian Pidgin, Hausa, Yoruba, or Igbo — via WhatsApp, with no app download required.

We are applying for grant funding of USD $25,000 to scale the platform from working prototype to 50,000 registered farmers across six Nigerian states within 12 months, while building Africa's first real-time multi-sector farm disease surveillance database covering crops, poultry, fish, and livestock.

# Problem Statement

- 33 million Nigerians projected to face food insecurity in 2025 (World Food Programme)

- Smallholder farmers produce approximately 80% of Nigeria's food (FAO) yet receive minimal support

- Post-harvest losses of 30–50% occur annually, largely due to undiagnosed crop and livestock disease

- The extension worker to farmer ratio in Nigeria is 1:3,000 — far below the recommended 1:400

- Only 5% of Sub-Saharan African farmers currently access any digital agricultural advisory service

When farmers cannot identify what is killing their crops, birds, or fish, they lose entire harvests, waste money on wrong treatments, or travel days to find an expert. AgroDoc AI eliminates this gap entirely.

# Proposed Solution

AgroDoc AI functions as an always-available AI extension worker accessible through WhatsApp. It is the only farm AI in Nigeria covering all four major farm sectors and all five major Nigerian languages including Pidgin English.

## How It Works

- Farmer sends 'hi' to the AgroDoc WhatsApp number — registration takes under 60 seconds (name + farm type)

- Farmer sends a photo or describes symptoms in their language — voice notes accepted

- Claude AI analyses the input and generates a personalised diagnosis with disease name, severity, and cause

- Farmer receives: 4-step treatment plan, recommended local Nigerian product, nearest agro-input shop

- Outbreak data aggregates automatically into Nigeria's first multi-sector disease surveillance map

## What Makes AgroDoc AI Unique

- First Nigerian farm AI to cover Crops + Poultry + Fish + Livestock in one platform

- First farm AI to support Nigerian Pidgin English — the most widely spoken daily language

- Farmer registration flow — every farmer identified by name and farm type for personalised care

- Offline-capable: 30 common disease profiles cached and functional without internet

- 19 security loopholes fixed — NDPR 2019 compliant, audit log, validated feedback loop

# Budget & Fund Utilisation

| Budget Line | Amount (USD) | % of Total |
| --- | --- | --- |
| AI API costs — Claude Sonnet (50,000 diagnoses/month × 12 months) | $7,200 | 29% |
| WhatsApp Business API setup and messaging infrastructure | $2,000 | 8% |
| Field agent salaries (6 states × 2 agents × 6 months) | $9,000 | 36% |
| Server infrastructure (Render / AWS) | $1,200 | 5% |
| Community onboarding events (farmer demo days, 6 states) | $3,000 | 12% |
| Monitoring, evaluation and reporting | $1,500 | 6% |
| Contingency (10%) | $1,100 | 4% |
| TOTAL | $25,000 | 100% |

# Implementation Timeline

| Period | Milestones |
| --- | --- |
| Month 1–2 | Deploy field agents in 6 states. Onboard first 1,000 registered farmers. Launch WhatsApp bot at scale. |
| Month 3–4 | Reach 10,000 registered users. Begin multi-sector outbreak map. First quarterly report. |
| Month 5–6 | Onboard 500 agro-dealers and vet extension workers. Partner with 2 state ADP offices. |
| Month 7–9 | Reach 30,000 registered farmers. Share anonymised outbreak data with IITA and FMARD. |
| Month 10–12 | Reach 50,000 registered farmers. Publish open-access Nigeria Farm Disease Dataset. Final report. |

# Sustainability Plan

- Sponsored product recommendations — agrochemical and veterinary companies pay ₦500K–₦2M/brand/year

- Agro-dealer and vet subscriptions — ₦3,000–₦5,000/month per professional for advanced Dealer Mode

- Data licensing — anonymised multi-sector outbreak data licensed to research institutions and government

Organisation: AgroDoc AI — Your Farm. Our Doctor.

Lead Applicant: Adegbegi Martins Maxwell

Email: adegbegimartinsmaxwell@gmail.com

Website: agrodoc.ng

Tech stack: React (web app), Node.js (backend), Claude AI (Anthropic), WhatsApp Cloud API, OpenStreetMap

Security: 19 loopholes fixed, NDPR 2019 compliant, audit log, validated feedback loop

|  | AgroDoc AI — Your Farm. Our Doctor. Adegbegi Martins Maxwell ¦ adegbegimartinsmaxwell@gmail.com ¦ agrodoc.ng |
| --- | --- |